## Potential Problems
Item | Problem Description | Probability | Impact | Severity
1 | Completion deadline not met | 1 | 10 | 10
2 | Data is corrupted or inaccurate | 3 | 7 | 21
3 | Data access is revoked for reporting on dashboard | 2 | 9 | 18
4 | Teammates fail to complete deliverables | 3 | 5 | 15
5 | Power Outage on due date of project | 2 | 4 | 8
6 | Tableau displays wrong data | 4 | 5 | 20
7 | Data feeds not uploading correctly/accurate | 5 | 3 | 15
8 | Tableau not working | 5 | 2 | 10
9 | Purchased laptops are not turning on | 2 | 7 | 14
10 | Underestimation of designed budget | 3 | 5 | 15

## Contingency PlansTriggers
Problem | Trigger | Contingency Plan
Data is corrupted or inaccurate | Dashboard not loading | Have backups of Data tables and tableau files that we can refer to
Tableau displays wrong data | Dashboard data looks off, or inaccurate | Save backups, and document all formulas and data sources to trace back
Data access is revoked for reporting on dashboard | Data source used no longer allowed for reporting data | Save data backups, but also have a separate source of data to reference in case primary data source loses access.
Data feeds not uploading correctly/accurate | Nothing shows on dashboard | Refresh or restart Tableau